## Capstone_Project_M01L02_RTM
Requirement ID | Requirement Description | Priority (MoSCoW) | Stakeholder(s) | Project Objective | Related Data File | Status
HF-R001 | If a data breach occurs, isolate affected systems immediately, notify IT security, and initiate root cause analysis. Apply emergency fixes and notify stakeholders. | Must Have | IT Security, Stakeholders | Maintain data security and integrity | N/A | Approved
HF-R002 | If staff resistance continues, deploy departmental change champions. Offer additional hands-on support and revise training strategies. | Must Have | Administrative Staff | Ensure smooth system adoption | N/A | Approved
HF-R003 | If scheduling system fails or causes delays, revert to manual scheduling as a backup. Prioritize urgent cases and engage IT to resolve issues quickly. | Must Have | IT Department, Administrative Staff | Minimize disruption to scheduling | N/A | Approved
HF-R004 | If wait times do not improve, increase front-desk staffing during peak hours and expand virtual consultation slots to redistribute load. | Must Have | Front-desk Staff, Patients | Improve patient wait times | N/A | Approved