## Sheet1
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Severity | Mitigation Strategy | Contingency Plan | Calculated Severity
HF-R001 | Sensitive patient data could be compromised during process changes. | Technical | Medium | High | High | Conduct regular data security audits; implement encryption; train staff on data protection policies. | If a data breach occurs, isolate affected systems immediately, notify IT security, and initiate root cause analysis. Apply emergency fixes and notify stakeholders. | High
HF-R002 | Staff may resist adopting new workflows due to insufficient training. | Operational | High | Medium | High | Run training sessions and feedback workshops; engage staff in workflow design. | If staff resistance continues, deploy departmental change champions. Offer additional hands-on support and revise training strategies. | High
HF-R003 | Inefficient appointment scheduling leading to a high rate of no-shows (17.78%) and cancellations (15.56%). | Operational | High | Medium | High | Deploy automated scheduling tools; align system rules with actual patient flow patterns. | If scheduling system fails or causes delays, revert to manual scheduling as a backup. Prioritize urgent cases and engage IT to resolve issues quickly. | High
HF-R004 | Long patient wait times (average 40.25 minutes) and negative feedback rate (25%) indicating potential dissatisfaction. | Operational | High | High | High | Streamline workflows; implement staggered appointments and digital check-ins. | If wait times do not improve, increase front-desk staffing during peak hours and expand virtual consultation slots to redistribute load. | High
HF-R005 | Staff may not receive adequate training on new workflows or technologies. | Operational | Medium | Medium | Medium | Monitor and manage; implement mitigation if severity increases. |  | Medium
HF-R006 | New or existing systems may experience unexpected downtime. | Technical | Low | High | Medium | Monitor and manage; implement mitigation if severity increases. |  | Medium
HF-R007 | Staff may not fully adopt the new workflows or technologies. | Stakeholder | Medium | Medium | Medium | Monitor and manage; implement mitigation if severity increases. |  | Medium
HF-R008 | Stakeholders may have differing or unclear expectations for the project. | Stakeholder | Low | Medium | Low | Monitor and manage; implement mitigation if severity increases. |  | Low
HF-R009 | Unavailability of resources (11.63%) may hinder timely patient care and service delivery. | Operational | Medium | Medium | Medium | Monitor and manage; implement mitigation if severity increases. |  | Medium
HF-R010 | Challenges in integrating new systems with existing infrastructure. | Technical | Low | Medium | Low | Monitor and manage; implement mitigation if severity increases. |  | Low